## Sheet1
|  | Apostolia | Despoina | Dimitris
Login/Logout |  | + |  |  | Done
Sign up |  | + |  |  | Done
Design |  | + | + | + | Done
Change account |  |  |  | +
Delete account |  |  | +
Συνδεδεμένοι Χρήστες |  | + | + | +
Add event |  |  |  | + | Done
Delete event |  |  | + |  | Done
Share event |  |  | + |  | Done
Change event |  |  |  | + | Done
Databases |  |  | + |  | Done
Word |  | + | + | + | Done
Final Word |  | + | + | +
Presentation |  | + | + | +
Usabilities |  | + | + | +
Testing |  |  | +
Meeting Date | Hours
Saturdays after class | 0,5
2016-11-14 | 2.5
2016-12-01 | 1
2016-12-12 | 2
2016-12-28 | 4
2016-12-29 | 2
2016-01-02 | 1.5